## Consolidated Est.
Task | Time (in hr)
Build user interest tables; tables will contain a list of interests from a predetermined list of 5 listed from most interested to least interested (maybe industries or activities) | 3
Build user stock tables; tables will contain a list of stocks that the user has selected for their account; list of 5? (store their full stock name and stock ticker symbol) | 4
Create table to display user inputs (front end) | 4
Collect data from the Yahoo Finance API on tasks the user is interested in (organize by two keys? stock ticker and date) | 3
Write a query that relates the user's list of stock and most recent stock information based on the stock ticker (add/remove function) | 5
Collect data from the Google News API and store data based on keywords from the title (keywords should be words relating to stock names or the predetermined lists of interests) | 3
Write a query that relates the user's list of stock and most recent news based on the stock ticker and interest words | 2
Collect data from the Twitter API and store data based on keywords from the title (keywords should be words relating to stock names or the predetermined lists of interests) | 3.5
search for relevant charts and graphs | 5
embed charts and graphs (partly front end) | 4
create a page to display stocks data | 5
create a page to display news | 5
Total | 46.5

## Anton
1) News API - 5hrs
- We will implement news API in order to obtain top X relevant news
- We can pass stock ticker and company name in order to request related news from Google News
- Currently displayed stories can be stored in some sort of DS which we will then implement in GUI
- We will also have set of currently displayed stories
- Once we receive GoogleNews response we will check have these stories already been seen (Are they already in our DS)
2) Fincance API - 5hrs
- We can initially create DS that will contain numerous values such as: Price,Volume,Open,High, ...
- We then send API request with stock name to Yahoo API
- Once Yahoo API returns values we populate our DS
3) Tweet API - 5hrs
- We create our DS (FIFO) that gets StockTwitAPI.
- We often/periodically request new tweet and check against our set that they haven't seen before
- Add new tweet to end of our DS

## Danielle
Tasks | Hours
Build user interest tables; tables will contain a list of interests from a predetermined list of 5 listed from most interested to least interested (maybe industries or activities) | 1
Build user stock tables; tables will contain a list of stocks that the user has selected for their account; list of 5? (store their full stock name and stock ticker symbol) | 2
Write a query to create a view relating the user's account, user's interest table, and user's stock table | 1
Collect data from the Yahoo Finance API on tasks the user is interested in (organize by two keys? stock ticker and date) | 3
Write a query that relates the user's list of stock and most recent stock information based on the stock ticker | 1
Collect data from the Google News API and store data based on keywords from the title (keywords should be words relating to stock names or the predetermined lists of interests) | 3
Write a query that relates the user's list of stock and most recent news based on the stock ticker and interest words | 1
Collect data from the Twitter API and store data based on keywords from the title (keywords should be words relating to stock names or the predetermined lists of interests) | 3
Write a query that relates the user's list of stock and most recent Tweets based on the stock ticker and interest words | 1
Develop the user interface | 5
21

## Kaelyn
Task | Time (in hr)
Build user input platform | 2
Add input to user profile (build storage space) | 4
Create table to display user inputs (front end) | 2
Create keyword search list | 3
Search for keywords in APIs | 2
Create display for the relevant articles (front end) | 4
Publish and embed the articles | 4
search for relevant charts and graphs | 5
embed charts and graphs (partly front end) | 4
embed self-refreshing twitter feed | 4
Total | 34

## Zhitong
build the login authentiation | 3 hours
design the home page | 3 hours
build the home page (including the watchlist) | 5 hours
utilize the Google News API | 2 hours
create the add/remove function (including an internal search bar) | 7 hours
build a dataset to store the watchlist | 5 hours
utilize the Yahoo Finance API | 2 hours
create a page to display stocks data | 5 hours
create a page to display news | 5 hours
37 hours